## Definition of Done
Level | ID | Criterion | How to check | Required
Story | S1 | Acceptance criteria met | Walk through each acceptance criterion on the story and confirm it works as written | Must
Story | S2 | Code reviewed | At least one other developer has approved the pull request | Must
Story | S3 | Tests written and passing | New code has unit tests and the full test suite passes | Must
Story | S4 | Merged and build green | Merged to the main branch and the CI build passes | Must
Story | S5 | QA tested on staging | Tested on the staging site by someone who didn't write it | Must
Story | S6 | No open critical bugs | No critical or high bugs left open against this story | Must
Story | S7 | Docs updated | User help, API docs or the README changed where needed | Should
Story | S8 | Product owner accepted | The product owner has seen it working and accepted it | Must
Sprint | SP1 | Only stories meeting the story DoD count | Points done on the Summary tab include only stories marked Done | Must
Sprint | SP2 | Sprint demo held | Finished work shown to stakeholders in the sprint review | Must
Sprint | SP3 | Unfinished stories moved back to backlog | Stories that are not done go back to the backlog, not counted as done | Must
Sprint | SP4 | Regression tests pass | Automated regression suite passes on staging | Must
Sprint | SP5 | Retrospective held, actions logged | Team retro done with at least one action item and an owner | Should
Release | R1 | Release notes written | Customer-facing notes cover new features and fixes | Must
Release | R2 | Performance check passed | Key pages and APIs load within your agreed targets | Must
Release | R3 | Security scan clean | Dependency and security scans show no high or critical issues | Must
Release | R4 | Rollback plan ready | Steps to roll back are written down and someone knows how to do it | Must
Release | R5 | Support team briefed | Support knows what's changing and has answers for likely questions | Should

## Story Checklist
Story ID | Story | Owner | Points | AC met | Reviewed | Tests pass | Merged | QA tested | No bugs | Docs | PO accepted | Checks | Status | Next missing
WEB-101 | Password reset by email | Maya | 5 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 8 | Done
WEB-102 | Show order history on account page | Ravi | 8 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | 7 | 1 to go | Docs
WEB-103 | Save cart between visits | Tom | 5 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 8 | Done
WEB-104 | Add Apple Pay at checkout | Maya | 13 | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | 4 | 4 to go | QA tested
WEB-105 | Fix tax rounding on invoices | Ravi | 2 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 8 | Done
WEB-106 | Product filter by size | Tom | 5 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2 | 6 to go | Tests pass
WEB-107 | Low stock badge on product page | Ana | 3 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 8 | Done
WEB-108 | Email receipt redesign | Ana | 5 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | FALSE | 6 | 2 to go | No bugs
WEB-109 | Speed up search results | Ravi | 8 | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 1 | 7 to go | Reviewed
WEB-110 | Accessibility fixes on checkout | Tom | 3 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | TRUE | 7 | 1 to go | Docs
WEB-111 | Gift card balance check | Maya | 3 | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 0 | Not started | AC met
WEB-112 | Update cookie banner text | Ana | 1 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 8 | Done

## Sprint and Release
Done | Level | ID | Criterion | Checked by | Date
TRUE | Sprint | SP1 | Only stories meeting the story DoD count | Ana | 2026-11-13
TRUE | Sprint | SP2 | Sprint demo held | Maya | 2026-11-13
TRUE | Sprint | SP3 | Unfinished stories moved back to backlog | Ravi | 2026-11-13
TRUE | Sprint | SP4 | Regression tests pass | Tom | 2026-11-12
FALSE | Sprint | SP5 | Retrospective held, actions logged
TRUE | Release | R1 | Release notes written | Ana | 2026-11-12
TRUE | Release | R2 | Performance check passed | Ravi | 2026-11-11
FALSE | Release | R3 | Security scan clean
FALSE | Release | R4 | Rollback plan ready
FALSE | Release | R5 | Support team briefed

## Summary
Criterion | Met | Not met | Rate
Acceptance criteria met | 11 | 1 | 91.67%
Code reviewed | 10 | 2 | 83.33%
Tests written and passing | 9 | 3 | 75%
Merged and build green | 9 | 3 | 75%
QA tested on staging | 8 | 4 | 66.67%
No open critical bugs | 7 | 5 | 58.33%
Docs updated | 6 | 6 | 50%
Product owner accepted | 7 | 5 | 58.33%
Stories in sprint | 12
Stories done | 5 |  | 41.67%
Points committed | 61
Points done | 16 |  | 26.23%
Sprint checks done | 4 | 1 | 80%
Release checks done | 2 | 3 | 40%