## Checklist
Done | Phase | Task | Owner | Days from start | Due | Status | Notes
TRUE | Before day 1 | Send offer letter and get it signed | HR | -21 | 2026-10-19 | Done
TRUE | Before day 1 | Run background check, if your company uses one | HR | -14 | 2026-10-26 | Done
TRUE | Before day 1 | Order laptop, monitor and headset | IT | -10 | 2026-10-30 | Done | Arrives Nov 4
TRUE | Before day 1 | Send payroll forms (W-4, direct deposit) | HR | -7 | 2026-11-02 | Done
TRUE | Before day 1 | Pick an onboarding buddy | Manager | -7 | 2026-11-02 | Done | Jamal
TRUE | Before day 1 | Send welcome email: start time, parking, dress code | Manager | -5 | 2026-11-04 | Done
TRUE | Before day 1 | Create email, Slack and system accounts | IT | -3 | 2026-11-06 | Done
TRUE | Before day 1 | Plan the first week's schedule | Manager | -3 | 2026-11-06 | Done
TRUE | Day 1 | Welcome, office tour and introductions | Buddy | 0 | 2026-11-09 | Done
TRUE | Day 1 | Complete Form I-9 and collect payroll forms | HR | 0 | 2026-11-09 | Done | Check I-9 deadlines with HR
TRUE | Day 1 | Set up laptop, passwords and sign-ins | IT | 0 | 2026-11-09 | Done
TRUE | Day 1 | Team lunch | Manager | 0 | 2026-11-09 | Done
FALSE | Day 1 | Go over the job description and 30-day goals | Manager | 0 | 2026-11-09 | Overdue | Rescheduled twice
TRUE | Week 1 | Shadow a teammate for a day | Buddy | 2 | 2026-11-11 | Done
TRUE | Week 1 | Benefits walkthrough and enrollment dates | HR | 3 | 2026-11-12 | Done
FALSE | Week 1 | Security and compliance training | New hire | 4 | 2026-11-13 | Overdue
FALSE | Week 1 | Meet key people one-on-one | New hire | 5 | 2026-11-14 | Overdue | 4 of 6 done
TRUE | Week 1 | End-of-week check-in | Manager | 4 | 2026-11-13 | Done
FALSE | Month 1 | Finish role-specific training | New hire | 9 | 2026-11-18 | Due soon
FALSE | Month 1 | Deliver a first small project | New hire | 21 | 2026-11-30 | Upcoming
FALSE | Month 1 | 30-day check-in with manager | Manager | 30 | 2026-12-09 | Upcoming
FALSE | Month 1 | Ask the new hire for onboarding feedback | HR | 30 | 2026-12-09 | Upcoming
FALSE | Months 2-3 | 60-day check-in | Manager | 60 | 2027-01-08 | Upcoming
FALSE | Months 2-3 | Set goals for the next quarter | Manager | 80 | 2027-01-28 | Upcoming
FALSE | Months 2-3 | 90-day review | Manager | 90 | 2027-02-07 | Upcoming
Formulas:
Due = IF(OR(ISBLANK([Task]),NOT(ISNUMBER([Days from start]))),"",'New Hire'!$B7+[Days from start])

## New Hire
Detail | Value | Notes
Name | Alex Rivera
Job title | Customer Success Specialist
Department | Customer Success
Manager | Karen Liu
Onboarding buddy | Jamal Brooks
Start date | 2026-11-09 | Every due date on the Checklist counts from this date
Today's date | 2026-11-16 | Type today's date, or =TODAY() to keep it current
Tasks done | 15 of 25
Progress | 60%
Overdue tasks | 3
Day of onboarding | Day 8 | Day 1 is the start date

## Progress
Phase or owner | Tasks | Done | Progress | Overdue | Due soon
Before day 1 | 8 | 8 | 100% | 0 | 0
Day 1 | 5 | 4 | 80% | 1 | 0
Week 1 | 5 | 3 | 60% | 2 | 0
Month 1 | 4 | 0 | 0% | 0 | 1
Months 2-3 | 3 | 0 | 0% | 0 | 0
By owner
HR | 6 | 5 | 83.33% | 0 | 0
Manager | 10 | 5 | 50% | 1 | 0
IT | 3 | 3 | 100% | 0 | 0
Buddy | 2 | 2 | 100% | 0 | 0
New hire | 4 | 0 | 0% | 2 | 1
All tasks | 25 | 15 | 60% | 3 | 1