## Overview
Item | Value
Event | Hope House Winter Benefit Dinner
Event date | 2027-01-30
Today (replace with =TODAY()) | 2026-10-18
Days to go | 104
Budget | 13500
Expected guests | 150
Booked with vendors | 12160
Paid so far | 2550
Left in budget | 1340
Cost per guest so far | 81.0667
Tasks done | 20%
Tasks overdue | 1
Tasks due in the next 2 weeks | 1
Vendors confirmed | 6 of 9

## Checklist
Weeks before | Due by | Task | Area | Owner | Done | Status | Notes
20 | 2026-09-12 | Set the goal, date and rough headcount | Planning | Jess | TRUE | Done
20 | 2026-09-12 | Set the total budget | Budget | Jess | TRUE | Done
18 | 2026-09-26 | Book the venue | Venue | Jess | TRUE | Done | Deposit paid
16 | 2026-10-10 | Recruit a planning team and split up jobs | People | Jess | TRUE | Done
16 | 2026-10-10 | Book the caterer | Food | Omar | TRUE | Done
15 | 2026-10-17 | Get event insurance and any permits | Admin | Jess | FALSE | Overdue | Venue needs certificate 30 days out
14 | 2026-10-24 | Book AV, music or a speaker | Program | Omar | FALSE | Next 2 weeks
14 | 2026-10-24 | Start finding sponsors | Money | Priya | TRUE | Done
12 | 2026-11-07 | Send save the dates | Guests | Priya | FALSE | Later
12 | 2026-11-07 | Set up ticketing or RSVPs | Guests | Priya | FALSE | Later
10 | 2026-11-21 | Order rentals: tables, chairs, linens | Venue | Omar | FALSE | Later
10 | 2026-11-21 | Collect auction items or prizes | Program | Dana | FALSE | Later
8 | 2026-12-05 | Send invitations | Guests | Priya | FALSE | Later
8 | 2026-12-05 | Design signs, programs and name tags | Printing | Dana | FALSE | Later
8 | 2026-12-05 | Promote on social media and email | Marketing | Priya | FALSE | Later
6 | 2026-12-19 | Book photographer | Program | Omar | FALSE | Later
6 | 2026-12-19 | Plan decor and order supplies | Decor | Dana | FALSE | Later
4 | 2027-01-02 | Write the run of show | Program | Jess | FALSE | Later
4 | 2027-01-02 | Recruit volunteers and assign shifts | People | Dana | FALSE | Later
3 | 2027-01-09 | Send printing to the printer | Printing | Dana | FALSE | Later
2 | 2027-01-16 | Give the caterer a final headcount | Food | Omar | FALSE | Later
2 | 2027-01-16 | Confirm every vendor's arrival time | Vendors | Omar | FALSE | Later
2 | 2027-01-16 | Seating chart, if seated | Guests | Priya | FALSE | Later
1 | 2027-01-23 | Send reminders to guests and volunteers | Guests | Priya | FALSE | Later
1 | 2027-01-23 | Pack the event day kit: tape, scissors, chargers, cash box | Day of | Dana | FALSE | Later
1 | 2027-01-23 | Walk through the venue with the team | Venue | Jess | FALSE | Later
0 | 2027-01-30 | Set up, check in vendors, run the event | Day of | Jess | FALSE | Later
-1 | 2027-02-06 | Pay final balances | Budget | Jess | FALSE | Later
-1 | 2027-02-06 | Send thank-yous to guests, sponsors and volunteers | Guests | Priya | FALSE | Later
-2 | 2027-02-13 | Team debrief: what worked and what to change | Planning | Jess | FALSE | Later
Formulas:
Due by = Overview!$B3-[Weeks before]*7

## Budget
Category | Planned | Booked | Paid so far | Left | Status
Venue | 2500 | 2400 | 600 | 100 | Within budget
Catering | 5000 | 5250 | 1000 | -250 | Over
Drinks | 1200 | 1300 | 0 | -100 | Over
Rentals | 1000 | 950 | 200 | 50 | Within budget
AV and music | 900 | 800 | 0 | 100 | Within budget
Decor | 500 | 420 | 420 | 80 | Within budget
Printing | 300 | 260 | 0 | 40 | Within budget
Photography | 600 | 600 | 150 | 0 | Within budget
Marketing | 250 | 0 | 0 | 250 | Nothing booked
Permits and insurance | 200 | 180 | 180 | 20 | Within budget
Prizes and gifts | 300 | 0 | 0 | 300 | Nothing booked
Contingency | 750 | 0 | 0 | 750 | Nothing booked
Total | 13500 | 12160 | 2550 | 1340 | Within budget

## Vendors
Category | Vendor | Contact | Phone | What they provide | Cost | Deposit paid | Paid in full | Paid so far | Balance | Confirmed | Arrives
Venue | Lakeview Community Hall | Karen Wills | (608) 555-0114 | Hall, kitchen, 8 hours | 2400 | 600 | FALSE | 600 | 1800 | TRUE | 15:00
Catering | Two Forks Catering | Omar Diaz | (608) 555-0152 | Buffet dinner for 150 | 5250 | 1000 | FALSE | 1000 | 4250 | TRUE | 15:30
Drinks | Corner Cellar | Sam Reyes | (608) 555-0177 | Wine, beer and soft drinks | 1300 | 0 | FALSE | 0 | 1300 | FALSE | 16:00
Rentals | Main Street Rentals | Tina Hall | (608) 555-0131 | Tables, chairs, linens | 950 | 200 | FALSE | 200 | 750 | TRUE | 10:00
AV and music | Bright Sound AV | Leo Park | (608) 555-0190 | Mic, speakers, projector | 800 | 0 | FALSE | 0 | 800 | FALSE | 14:00
Decor | Online order |  |  | Centerpieces and lights | 420 | 420 | TRUE | 420 | 0 | TRUE
Printing | QuickPrint |  | (608) 555-0108 | Programs, signs, name tags | 260 | 0 | FALSE | 0 | 260 | FALSE
Photography | Ana Cruz Photo | Ana Cruz | (608) 555-0165 | 3 hours of coverage | 600 | 150 | FALSE | 150 | 450 | TRUE | 17:30
Permits and insurance | Event Shield | Online |  | One-day liability policy | 180 | 180 | TRUE | 180 | 0 | TRUE

## Day-of Schedule
Time | What happens | Who | Where | Done
10:00 | Rentals delivered and set up | Omar | Main hall | FALSE
13:00 | Planning team arrives, decor goes up | Dana | Main hall | FALSE
14:00 | AV setup and sound check | Leo (AV) | Stage | FALSE
15:00 | Venue walk-through with the manager | Jess | Whole venue | FALSE
15:30 | Caterer arrives and sets up | Omar | Kitchen | FALSE
16:30 | Volunteers arrive, briefing | Dana | Lobby | FALSE
17:00 | Check-in table opens | Priya | Lobby | FALSE
17:30 | Doors open, drinks and photos | Jess | Main hall | FALSE
18:15 | Welcome and thank-you to sponsors | Jess | Stage | FALSE
18:30 | Dinner served | Omar | Main hall | FALSE
19:30 | Program and raffle | Jess | Stage | FALSE
20:30 | Event ends, guests leave | Everyone | Main hall | FALSE
20:45 | Teardown and load out | Everyone | Whole venue | FALSE
22:00 | Venue cleared, keys returned | Jess | Front desk | FALSE