## Gantt Chart
Task | Phase | Owner | Start | End | Workdays | Done | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | Done days
Week of | [7 empty] | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14 | 12/21 | 12/28 | 1/4 | 1/11 | 1/18
Kickoff meeting | Plan | Dana | 2026-11-02 | 2026-11-02 | 1 | 100% | Done | [12 empty] | 1 | bar: 11/2
Gather requirements | Plan | Dana | 2026-11-02 | 2026-11-06 | 5 | 100% | Done | [12 empty] | 5 | bar: 11/2
Site map and content plan | Plan | Priya | 2026-11-09 | 2026-11-13 | 5 | 100% | Done | [12 empty] | 5 | bar: 11/9
Wireframes | Design | Marcus | 2026-11-16 | 2026-11-25 | 8 | 80% | Late | [12 empty] | 6.4 | bar: 11/16 to 11/23
Visual design | Design | Marcus | 2026-11-23 | 2026-12-04 | 10 | 40% | In progress | [12 empty] | 4 | bar: 11/23 to 11/30
Design sign-off | Design | Dana | 2026-12-04 | 2026-12-04 | 1 | 0% | Not started | [12 empty] | 0 | bar: 11/30
Front-end build | Build | Leo | 2026-12-07 | 2026-12-23 | 13 | 0% | Not started | [12 empty] | 0 | bar: 12/7 to 12/21
CMS setup | Build | Leo | 2026-12-07 | 2026-12-18 | 10 | 0% | Not started | [12 empty] | 0 | bar: 12/7 to 12/14
Write and load content | Build | Priya | 2026-12-14 | 2027-01-08 | 20 | 0% | Not started | [12 empty] | 0 | bar: 12/14 to 1/4
QA testing | Test | Priya | 2027-01-04 | 2027-01-13 | 8 | 0% | Not started | [12 empty] | 0 | bar: 1/4 to 1/11
Fix bugs | Test | Leo | 2027-01-11 | 2027-01-15 | 5 | 0% | Not started | [12 empty] | 0 | bar: 1/11
Client review | Test | Dana | 2027-01-14 | 2027-01-18 | 3 | 0% | Not started | [12 empty] | 0 | bar: 1/11 to 1/18
Launch day | Launch | Leo | 2027-01-20 | 2027-01-20 | 1 | 0% | Not started | [12 empty] | 0 | bar: 1/18
Post-launch checks | Launch | Priya | 2027-01-20 | 2027-01-22 | 3 | 0% | Not started | [12 empty] | 0 | bar: 1/18
Formulas:
Workdays = IF(AND(ISNUMBER([Start]),ISNUMBER([End])),NETWORKDAYS([Start],[End]),"")

## Summary
Item | Value | Notes
Today's date | 2026-11-30 | Type a new date, or =TODAY() to keep it current
Chart starts (week of) | 2026-11-02 | The Monday of your first task's week. Type a date to start the chart somewhere else
Project start | 2026-11-02
Project finish | 2027-01-22
Workdays start to finish | 60 | Mondays to Fridays, holidays not taken out
Workdays left | 40
Tasks | 14
Done | 3
In progress | 1
Late | 1 | Past the end date and not at 100%
Overall progress | 23.01% | Each task's Done % weighted by its workdays
Formulas:
Value = NETWORKDAYS(B4,[Value, row above])

## By Phase
Phase | Tasks | Done | Late | Workdays | Progress
Plan | 3 | 3 | 0 | 11 | 100%
Design | 3 | 0 | 1 | 19 | 54.74%
Build | 3 | 0 | 0 | 43 | 0%
Test | 3 | 0 | 0 | 16 | 0%
Launch | 2 | 0 | 0 | 4 | 0%
All phases | 14 | 3 | 1 | 93 | 23.01%