## Issue Log
ID | Issue | Area | Priority | Reported by | Owner | Opened | Target date | Stage | Resolved on | Next step or fix | Days open | Status | Open days (helper)
ISS-001 | Two desks in the new office have no network ports | IT | High | Rachel Kim | Ben Ortiz | 2026-10-05 | 2026-10-09 | Done | 2026-10-08 | Electrician added two ports | 3 | Resolved | 0
ISS-002 | Movers quote came in $1,800 over budget | Budget | High | Ben Ortiz | Laura Simms | 2026-10-06 | 2026-10-13 | Done | 2026-10-12 | Second quote accepted, $400 under budget | 6 | Resolved | 0
ISS-003 | Printer won't connect to the new Wi-Fi | IT | Medium | Front desk | Ben Ortiz | 2026-10-12 | 2026-10-14 | Done | 2026-10-16 | Firmware update, then reconnected | 4 | Resolved late | 0
ISS-004 | Conference room blinds missing | Facilities | Low | Rachel Kim | Tara Jones | 2026-10-13 | 2026-10-30 | Done | 2026-10-27 | Landlord installed them | 14 | Resolved | 0
ISS-005 | Shared drive permissions lost after the server move | IT | Critical | Accounts team | Ben Ortiz | 2026-10-19 | 2026-10-20 | Done | 2026-10-20 | Restored folder permissions from last week's backup | 1 | Resolved | 0
ISS-006 | Parking passes not issued for 4 staff | Facilities | Medium | Daniel Wu | Tara Jones | 2026-10-20 | 2026-10-27 | Waiting |  | Building manager ordering the passes | 17 | Overdue | 17
ISS-007 | Phone system drops calls transferred to sales | Vendors | High | Sales team | Ben Ortiz | 2026-10-21 | 2026-10-28 | In progress |  | Ticket open with the phone provider (#58213) | 16 | Overdue | 16
ISS-008 | Kitchen fridge leaking water | Facilities | Medium | Maya Patel | Tara Jones | 2026-10-26 | 2026-11-02 | Done | 2026-11-04 | Replaced the water line | 9 | Resolved late | 0
ISS-009 | New hires can't log in to the payroll portal | Staff | High | Laura Simms | Laura Simms | 2026-10-28 | 2026-11-04 | In progress |  | Waiting on the payroll company to reset accounts | 9 | Overdue | 9
ISS-010 | Office cleaning only happening twice a week, not three | Vendors | Low | Rachel Kim | Tara Jones | 2026-10-29 | 2026-11-13 | Not started |  | Check the contract, then call the cleaning company | 8 | On track | 8
ISS-011 | Laptop docking stations flicker on two monitors | IT | Medium | Daniel Wu | Ben Ortiz | 2026-11-02 | 2026-11-06 | In progress |  | Testing a new cable on one desk | 4 | Due soon | 4
ISS-012 | Signage on the street door still shows the old suite number | Facilities | Low | Front desk | Tara Jones | 2026-11-03 | 2026-11-20 | Not started |  | Get a quote from the sign shop | 3 | On track | 3
ISS-013 | Furniture invoice billed for 12 chairs, only 10 delivered | Budget | Medium | Laura Simms | Laura Simms | 2026-11-04 | 2026-11-11 | Waiting |  | Emailed the supplier for a corrected invoice | 2 | On track | 2
ISS-014 | VPN slow for remote staff since the move | IT | High | Remote team | Ben Ortiz | 2026-11-05 | 2026-11-07 | Not started |  | Check the new firewall settings | 1 | Due soon | 1
ISS-015 | Emergency exit map not posted on the second floor | Facilities | High | Maya Patel | Tara Jones | 2026-11-05 | 2026-11-09 | In progress |  | Map printed, framing on order | 1 | Due soon | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Summary
Item | Count
Today's date | 2026-11-06
Issues logged | 15
Open | 9
Overdue | 3
Due in the next 3 days | 3
Resolved | 6
Resolved late | 2
Average days to resolve | 6.2
Oldest open issue (days) | 17
Open by priority
Critical | 0
High | 4
Medium | 3
Low | 2
Open by owner
Ben Ortiz | 3
Tara Jones | 4
Laura Simms | 2
Open by area
IT | 2
Facilities | 3
Vendors | 2
Staff | 1
Budget | 1