## Quote
QUOTE
Brightside Remodeling LLC | Quote no. | Q-2026-118
1520 Lakeview Rd, Madison, WI 53704 | Quote date | 2026-10-14
(608) 555-0193 ¦ quotes@brightsideremodel.com | Valid for (days) | 30
| Valid until | 2026-11-13
Prepared for | Quote total | 8586.64
Karen and Mike Sullivan
418 Birch St, Madison, WI 53711
ksullivan@email.com ¦ (608) 555-0127
Job: Hall bathroom remodel. Replace tub with tiled walk-in shower, new tile floor, vanity, toilet and exhaust fan.
What's included |  | Price
Labor |  | 4218.75
Materials |  | 2718
Equipment and disposal |  | 713
Subcontractors |  | 528
| Subtotal | 8177.75
| Sales tax rate | 5%
| Sales tax | 408.89
| Total | 8586.64
| Deposit to book | 30%
| Deposit due | 2575.99
| Due on completion | 6010.65
Estimated time on site: 2 to 3 weeks. Start date set when the deposit is received.
Prices are good until the Valid until date. Changes to the scope are quoted separately before work starts.
Accepted by (signature and date):
Formulas:
Q-2026-118 = D3+[Q-2026-118, row above]

## Estimate
Section | Item | Qty | Unit | Unit cost | Your cost | Markup | Price | Profit
Labor | Demo old tub, tile and vanity | 10 | hours | 55 | 550 | 25% | 687.5 | 137.5
Labor | Rough plumbing for new shower valve | 6 | hours | 85 | 510 | 25% | 637.5 | 127.5
Labor | Install cement board and waterproofing | 8 | hours | 55 | 440 | 25% | 550 | 110
Labor | Tile walls and floor | 22 | hours | 60 | 1320 | 25% | 1650 | 330
Labor | Set vanity, toilet and fixtures | 6 | hours | 55 | 330 | 25% | 412.5 | 82.5
Labor | Paint and trim | 5 | hours | 45 | 225 | 25% | 281.25 | 56.25
Materials | Porcelain wall and floor tile | 120 | sq ft | 4.25 | 510 | 20% | 612 | 102
Materials | Thinset, grout and waterproofing | 1 | lot | 310 | 310 | 20% | 372 | 62
Materials | Cement board and screws | 10 | sheets | 16.5 | 165 | 20% | 198 | 33
Materials | Shower valve and trim kit | 1 | each | 285 | 285 | 20% | 342 | 57
Materials | 36 in vanity with top | 1 | each | 640 | 640 | 20% | 768 | 128
Materials | Toilet | 1 | each | 260 | 260 | 20% | 312 | 52
Materials | Paint, caulk and trim | 1 | lot | 95 | 95 | 20% | 114 | 19
Equipment and disposal | Dumpster, 10 yard | 1 | each | 425 | 425 | 15% | 488.75 | 63.75
Equipment and disposal | Tile saw rental | 3 | days | 65 | 195 | 15% | 224.25 | 29.25
Subcontractors | Electrician: GFCI outlet and exhaust fan | 1 | job | 480 | 480 | 10% | 528 | 48

## Job Profit
Item | Amount
Your cost | 6740
Price to customer (before tax) | 8177.75
Profit | 1437.75
Profit margin | 17.58%
Overall markup | 21.33%
Labor hours | 57
Labor cost | 3375
Materials cost | 2265
Equipment and disposal cost | 620
Subcontractor cost | 480
Lines not in a section | 0