## RAID Log
RAID Log | [8 empty] | rowsandcells.com
Risks, assumptions, issues and dependencies in one list. | [8 empty] | Free template
ID | Type | Description | Owner | Priority | Raised on | Due date | Status | Next action | Closed on | Days open | Flag
R-01 | Risk | Old customer records have duplicates, so the import creates messy data | Tom Reyes | High | 2026-08-10 | 2026-10-30 | In progress | Run the dedupe on a copy; sales reviews the merge list |  | 69 | On track
R-02 | Risk | Sales reps keep using the old spreadsheet after go-live | Priya Nair | High | 2026-08-12 | 2026-12-15 | Open | Make the old sheet read-only on go-live day |  | 67 | On track
R-03 | Risk | Email sync fails for reps on older laptops | Tom Reyes | Medium | 2026-08-20 | 2026-11-13 | In progress | Test on the three oldest laptops |  | 59 | On track
R-04 | Risk | Licence costs rise at renewal next year | Jake Morris | Low | 2026-08-25 | 2027-01-15 | Open | Ask for a two-year price lock in the contract |  | 54 | On track
R-05 | Risk | Our only CRM admin is away during go-live week | Sara Kim | Medium | 2026-09-02 | 2026-11-20 | Open | Train Lena as backup admin |  | 46 | On track
R-06 | Risk | Go-live slips past Nov 30 and clashes with year-end | Sara Kim | High | 2026-09-15 | 2026-11-06 | In progress | Weekly checkpoint with the vendor; fallback date Jan 11 |  | 33 | On track
R-07 | Risk | Data export from the old system takes longer than planned | Tom Reyes | High | 2026-09-28 | 2026-10-16 | Open | Book a second export window |  | 20 | Overdue
A-01 | Assumption | All 24 reps can attend two half-day training sessions in November | Priya Nair | High | 2026-08-10 | 2026-10-24 | Open | Confirm dates with each team lead |  | 69 | Due this week
A-02 | Assumption | The old system's export includes notes and attachments | Tom Reyes | High | 2026-08-10 | 2026-09-30 | Closed | Logged as issue I-03 | 2026-09-29 | 50 | Closed
A-03 | Assumption | The quoting tool can connect through the CRM's standard API | Tom Reyes | Medium | 2026-08-18 | 2026-10-20 | Open | Run a test connection in the sandbox |  | 61 | Due this week
A-04 | Assumption | Finance approves the extra $6,000 for data cleanup | Jake Morris | High | 2026-08-25 | 2026-09-15 | Closed | Approved at the September budget meeting | 2026-09-14 | 20 | Closed
A-05 | Assumption | Sales managers will run weekly pipeline reviews in the CRM | Priya Nair | Medium | 2026-09-05 | 2026-12-01 | Open | Agree the meeting format with the managers |  | 43 | On track
A-06 | Assumption | The vendor's standard onboarding covers our custom fields | Lena Fox | Low | 2026-09-20 | 2026-10-31 | Closed | Confirmed on the onboarding call | 2026-10-08 | 18 | Closed
I-01 | Issue | IT team still has no sandbox access | Tom Reyes | High | 2026-09-08 | 2026-09-19 | Closed | Vendor reset the admin accounts | 2026-09-18 | 10 | Closed
I-02 | Issue | Custom field list doesn't match how sales actually works | Priya Nair | Medium | 2026-09-12 | 2026-10-10 | In progress | Workshop with two reps to trim the list |  | 36 | Overdue
I-03 | Issue | Export is missing notes and attachments | Tom Reyes | High | 2026-09-29 | 2026-10-23 | In progress | Provider runs a full backup export; check the file Oct 22 |  | 19 | Due this week
I-04 | Issue | Training room booked for the wrong week | Lena Fox | Low | 2026-10-05 | 2026-10-09 | Closed | Rebooked for Nov 9 and 10 | 2026-10-07 | 2 | Closed
I-05 | Issue | Two pilot reps can't log in | Tom Reyes | High | 2026-10-14 | 2026-10-16 | Open | Reset passwords and check the licences |  | 4 | Overdue
I-06 | Issue | Pilot users say the mobile app is slow on site visits | Priya Nair | Medium | 2026-10-12 | 2026-11-02 | Waiting | Support ticket open with the vendor |  | 6 | On track
D-01 | Dependency | Vendor sets up the production account | Lena Fox | High | 2026-08-15 | 2026-10-21 | Waiting | Signed order sent Oct 1; chase on Oct 20 |  | 64 | Due this week
D-02 | Dependency | Final data export from the old CRM provider | Tom Reyes | High | 2026-08-20 | 2026-11-13 | Open | Export window booked for Nov 12 |  | 59 | On track
D-03 | Dependency | Web agency connects the website form to the CRM | Tom Reyes | Medium | 2026-09-01 | 2026-11-20 | Open | Send the agency the API key and field map |  | 47 | On track
D-04 | Dependency | Finance sets up the new price list before go-live | Jake Morris | Medium | 2026-09-10 | 2026-11-16 | In progress | Draft list due Nov 2 |  | 38 | On track
D-05 | Dependency | IT supplier replaces the five oldest laptops | Tom Reyes | Low | 2026-08-28 | 2026-10-01 | Closed | Delivered and set up | 2026-09-30 | 33 | Closed
D-06 | Dependency | Contract signed with the CRM vendor | Jake Morris | High | 2026-08-05 | 2026-08-29 | Closed | Signed Aug 27 | 2026-08-27 | 22 | Closed

## Summary
Summary |  |  | rowsandcells.com
Worked out from your other tabs. Shaded cells are formulas: nothing to type here. |  |  | Free template
Item | Logged | Open | High open | Overdue | Due in 7 days
Today's date | 2026-10-18
Risk | 7 | 7 | 4 | 1 | 0
Assumption | 6 | 3 | 1 | 0 | 2
Issue | 6 | 4 | 2 | 2 | 1
Dependency | 6 | 4 | 2 | 0 | 1
All types | 25 | 18 | 9 | 3 | 4
Open by owner
Sara Kim | 2 | 2 | 1 | 0 | 0
Tom Reyes | 11 | 8 | 5 | 2 | 2
Priya Nair | 5 | 5 | 2 | 1 | 1
Jake Morris | 4 | 2 | 0 | 0 | 0
Lena Fox | 3 | 1 | 1 | 0 | 1

## RAID Guide
RAID Guide |  | rowsandcells.com
Type in the cream cells. Shaded cells are formulas and fill in on their own. |  | Free template
Type | What it is | Example | What to record
Risk | Something that might happen and would hurt the project if it did | Data export takes longer than planned | Owner, priority, the action that makes it less likely, and a date to check it again
Assumption | Something you're treating as true without proof yet | All reps can attend training in November | Who will confirm it and by when. If it turns out wrong, close it and log a risk or issue
Issue | A problem that is happening now and needs fixing | Two pilot users can't log in | Owner, priority, the fix and the date it must be fixed by
Dependency | Something you need from another team, supplier or task before you can move on | Vendor sets up the production account | Who you depend on, the date you need it, and who chases it