## Risk Log
ID | Risk | Category | Owner | Likelihood (1-5) | Impact (1-5) | Score | Rating | Response plan | Action due | Status | Likelihood after | Impact after | Score after | Review flag
R-01 | Contractor finishes the build-out late and opening slips | Schedule | Jen Walsh | 4 | 4 | 16 | High | Weekly site walk with the contractor. Late penalty written into the contract. | 2026-11-13 | In progress | 3 | 3 | 9 | Due in 2 weeks
R-02 | Build-out costs run over budget | Budget | Marcus Hale | 3 | 4 | 12 | Medium | Keep a 10% contingency. Approve every change order in writing first. | 2026-11-20 | Open | 2 | 3 | 6 | Due in 2 weeks
R-03 | Health inspection fails on the first visit | Compliance | Jen Walsh | 2 | 5 | 10 | Medium | Book a pre-inspection walk-through with a food safety consultant. | 2026-12-01 | Open | 1 | 5 | 5 | On track
R-04 | Espresso machine delivery delayed by a supplier backorder | Suppliers | Jen Walsh | 3 | 3 | 9 | Medium | Confirm the ship date. Ask the supplier about a loaner machine. | 2026-11-02 | Open | 2 | 2 | 4 | Action overdue
R-05 | Can't hire enough baristas before opening day | People | Alicia Moreno | 4 | 4 | 16 | High | Post jobs 6 weeks out. $200 referral bonus for staff. | 2026-11-09 | In progress | 3 | 3 | 9 | Due in 2 weeks
R-06 | New staff quit during the training weeks | People | Alicia Moreno | 2 | 3 | 6 | Low | Pay for training shifts. Pair each new hire with a lead. | 2026-11-27 | Open | 2 | 2 | 4 | On track
R-07 | Point-of-sale system not set up in time | Equipment and tech | Devon Price | 2 | 4 | 8 | Medium | Install and test 2 weeks before opening. Keep a card reader as backup. | 2026-11-30 | Open | 1 | 3 | 3 | On track
R-08 | Internet not installed by opening day | Equipment and tech | Devon Price | 3 | 4 | 12 | Medium | Booked the install early. Phone hotspot as backup. | 2026-10-30 | Closed | 1 | 2 | 2 | Closed
R-09 | Customers slip at the new entrance in winter | Safety | Marcus Hale | 3 | 3 | 9 | Medium | Heavy-duty mats and an ice-melt contract with the landlord. | 2026-11-27 | Open | 1 | 3 | 3 | On track
R-10 | Grand opening clashes with road work on Main St | Schedule | Marcus Hale | 2 | 3 | 6 | Low | Checked the city road work calendar. No work planned that week. | 2026-10-23 | Closed | 1 | 3 | 3 | Closed
R-11 | Sales are slower than forecast for the first 3 months | Budget | Marcus Hale | 3 | 5 | 15 | High | Keep 3 months of rent in reserve. Plan opening promos and a loyalty card. | 2026-12-15 | Open | 2 | 4 | 8 | On track
R-12 | Sign permit not approved before opening | Compliance | Jen Walsh | 3 | 2 | 6 | Low | Applied early. Temporary banner as a backup. | 2026-11-05 | In progress | 1 | 2 | 2 | Action overdue
R-13 | Walk-in cooler fails and stock spoils | Equipment and tech | Devon Price | 2 | 4 | 8 | Medium | Service contract plus a temperature alarm that texts the manager. | 2026-12-04 | Open | 1 | 3 | 3 | On track
R-14 | Key supplier raises milk and bean prices | Suppliers | Alicia Moreno | 3 | 3 | 9 | Medium | Get a quote from a second supplier. Review menu prices in January. | 2027-01-15 | Open | 3 | 2 | 6 | On track

## Heat Map
Likelihood | Impact 1 | Impact 2 | Impact 3 | Impact 4 | Impact 5 | Open risks | Level
5 Almost certain | 0 | 0 | 0 | 0 | 0 | 0 | 5
4 Likely | 0 | 0 | 0 | 2 | 0 | 2 | 4
3 Possible | 0 | 1 | 3 | 1 | 1 | 6 | 3
2 Unlikely | 0 | 0 | 1 | 2 | 1 | 4 | 2
1 Rare | 0 | 0 | 0 | 0 | 0 | 0 | 1
Total | 0 | 1 | 4 | 5 | 2 | 12

## Summary
Item | Value
Today's date | 2026-11-06
High rating at or above | 15
Medium rating at or above | 8
Risks logged | 14
Open risks | 12
Closed risks | 2
Open and rated High | 3
Open and rated Medium | 7
Open and rated Low | 2
Actions overdue | 2
Actions due in 2 weeks | 3
Total open score now | 124
Total open score after actions | 62
Open risks by category
Schedule | 1
Budget | 2
People | 2
Suppliers | 2
Compliance | 2
Equipment and tech | 2
Safety | 1

## Scoring Guide
Score | Likelihood | Impact
1 | Rare: very unlikely to happen | Minor: barely noticed, fixed in a day
2 | Unlikely: could happen, but wouldn't be expected | Small: a short delay or a cost that's easy to absorb
3 | Possible: about as likely as not | Moderate: a noticeable delay or cost that needs a plan
4 | Likely: would not be a surprise | Major: a big delay, cost or hit to your reputation
5 | Almost certain: expected to happen | Severe: stops the project or causes serious harm