## Overview
Wedding date | Total budget | Guests (estimate) | Estimated cost | Booked | Paid so far | Still owed | Budget not booked | Checklist done
2027-06-12 | 35000 | 120 | 33000 | 26700 | 7500 | 19200 | 8300 | 24.24%

## Checklist
Months before | Due by | Task | Area | Who | Done | Notes
12 | 2026-06-12 | Set your total budget | Budget | Both | TRUE
12 | 2026-06-12 | Draft a guest list and rough headcount | Guests | Both | TRUE
12 | 2026-06-12 | Pick a date and book the venue | Venue | Both | TRUE
11 | 2026-07-13 | Book the photographer | Vendors | Maya | TRUE
10 | 2026-08-12 | Book the caterer (if not with the venue) | Vendors | Daniel | TRUE
10 | 2026-08-12 | Choose your wedding party | People | Both | TRUE
9 | 2026-09-11 | Book the officiant | Vendors | Both | TRUE
9 | 2026-09-11 | Book a DJ or band | Vendors | Daniel | FALSE
9 | 2026-09-11 | Make a wedding website | Guests | Maya | FALSE
8 | 2026-10-12 | Shop for wedding dress or suit | Attire | Maya | TRUE
8 | 2026-10-12 | Reserve a hotel room block for guests | Guests | Daniel | FALSE
8 | 2026-10-12 | Send save the dates | Guests | Both | FALSE
7 | 2026-11-11 | Book the florist | Vendors | Maya | FALSE
6 | 2026-12-12 | Book hair and makeup | Vendors | Maya | FALSE
6 | 2026-12-12 | Order the cake | Vendors | Both | FALSE
6 | 2026-12-12 | Rent tables, chairs and linens | Vendors | Daniel | FALSE
5 | 2027-01-11 | Set up a gift registry | Guests | Both | FALSE
4 | 2027-02-10 | Book transportation | Vendors | Daniel | FALSE
4 | 2027-02-10 | Plan the rehearsal dinner | Events | Both | FALSE
4 | 2027-02-10 | Buy wedding rings | Attire | Both | FALSE
3 | 2027-03-13 | Order invitations | Guests | Maya | FALSE
3 | 2027-03-13 | First dress or suit fitting | Attire | Maya | FALSE
2 | 2027-04-12 | Mail invitations | Guests | Both | FALSE
2 | 2027-04-12 | Apply for the marriage license (check your state's timing) | Legal | Both | FALSE
2 | 2027-04-12 | Finalize the ceremony with your officiant | Ceremony | Both | FALSE
1 | 2027-05-13 | Give the final headcount to the caterer | Guests | Daniel | FALSE
1 | 2027-05-13 | Make the seating chart | Guests | Both | FALSE
1 | 2027-05-13 | Confirm times with every vendor | Vendors | Maya | FALSE
0.5 | 2027-05-28 | Write vows and toasts | Ceremony | Both | FALSE
0.5 | 2027-05-28 | Final fitting and pick up attire | Attire | Maya | FALSE
0.25 | 2027-06-04 | Pay final balances and prep vendor tips | Budget | Daniel | FALSE
0.25 | 2027-06-04 | Pack for the honeymoon | Honeymoon | Both | FALSE
0 | 2027-06-12 | Hand off the day-of timeline and rings | Day of | Both | FALSE
Formulas:
Due by = Overview!$A2-ROUND([Months before]*30.4,0)

## Budget
Category | Estimated | Booked | Paid so far | Still owed | Under or over
Venue | 10000 | 9800 | 3000 | 6800 | 200
Catering | 8000 | 7600 | 1500 | 6100 | 400
Photography | 3200 | 3400 | 1000 | 2400 | -200
Music | 1500 | 1400 | 0 | 1400 | 100
Flowers | 2000 | 2200 | 0 | 2200 | -200
Attire | 2000 | 1850 | 1850 | 0 | 150
Hair and makeup | 600 | 0 | 0 | 0
Cake | 600 | 0 | 0 | 0
Officiant | 400 | 450 | 150 | 300 | -50
Rings | 1800 | 0 | 0 | 0
Invitations | 500 | 0 | 0 | 0
Rentals | 1200 | 0 | 0 | 0
Transportation | 500 | 0 | 0 | 0
Other | 700 | 0 | 0 | 0
Total | 33000 | 26700 | 7500 | 19200 | 400

## Vendors
Category | Company | Contact | Phone | Email | Contract signed | Total cost | Deposit paid | Paid in full | Balance due | Balance due by
Venue | Willow Creek Barn | Sara Holt | (503) 555-0110 | events@willowcreekbarn.com | TRUE | 9800 | 3000 | FALSE | 6800 | 2027-05-12
Catering | Harvest Table Catering | Mike Russo | (503) 555-0135 | mike@harvesttable.com | TRUE | 7600 | 1500 | FALSE | 6100 | 2027-05-29
Photography | Lena Ford Photo | Lena Ford | (971) 555-0177 | hello@lenafordphoto.com | TRUE | 3400 | 1000 | FALSE | 2400 | 2027-05-29
Attire | Bella Bridal | Jen Cole | (503) 555-0191 | jen@bellabridal.com | TRUE | 1850 | 1850 | TRUE | 0
Officiant | Rev. Grace Lin | Grace Lin | (503) 555-0122 | gracelin@email.com | TRUE | 450 | 150 | FALSE | 300 | 2027-06-12
Music | Spin City DJs | Andre Banks | (503) 555-0166 | book@spincitydjs.com | FALSE | 1400 | 0 | FALSE | 1400
Flowers | Petal and Stem | Rosa Diaz | (503) 555-0104 | rosa@petalandstem.com | FALSE | 2200 | 0 | FALSE | 2200